## Feuille 1
DETAILS |  |  | Release Objectives |  |  |  | TWCC Instance Results |  |  | Burundi Results
Start Date | [5 empty] | Pass | Pass | Pass - Signed in through the Continue with Admin OAuth flow and landed on /isoko/association with the Associations dashboard heading visible. |  | Pass | #ERROR! |  |  | 2026-06-18 23:33 | 2026-06-18 23:33
App Version: | [5 empty] | Pass | Pending Testing | Pass - Submitted a wrong password; the flow stayed on the OAuth host, surfaced an invalid-credentials error, and never reached the dashboard. |  | Pending Testing | #ERROR! |  |  | 2026-06-18 23:33 | 2026-06-18 23:33
Release Date: | [5 empty] | Pending Testing | Fail | Blocked - test data unavailable: no deactivated admin account provisioned (primary admin only). |  | Fail | #ERROR!
Current Status | 3. Testing (3 Days) |  |  |  |  | Pending Testing | Total Test Cases | Blocked - test data unavailable: no non-admin / second-role account provisioned (primary admin only). |  | Total Test Cases | #ERROR!
Overall Recommendation | Testing Ongoing |  |  |  |  | Pending Testing |  | Blocked - requires a second device/session or restricted user; not automatable with a single primary admin.
[6 empty] | Pass |  | Pass - Deep-linked to a protected admin route while logged out and was bounced to the sign-in / OAuth page instead of seeing the data. | [5 empty] | 2026-06-18 23:33 | 2026-06-18 23:33
[6 empty] | Pass |  | Pass - Dashboard renders the Total Associations, Active Associations and Pending Approval metric cards with at least one numeric value. | [5 empty] | 2026-06-18 23:33 | 2026-06-18 23:33
Test Case ID | Test case Title | Pre-condition | Test Steps | Expect Result | Developer status | Fail | Recommendation | Fail - No top-rated section (top sellers, top products, or highest-rated) is rendered on the instance admin dashboard. (runtime: Error: No "top rated" section is present on the instance admin dashboard) | start date |  |  | Comment | Expected Completion Date | 2026-06-18 23:33 | 2026-06-18 23:33
LOG IN | [5 empty] | Fail |  | Fail - All core sidebar entries (Users, Orders, Roles, Products, Locations) are available, and navigating to Users and Orders loads their pages. did not behave as expected (runtime: Error: Sidebar entry "Users" should be available) |  | In-progress |  |  |  | 2026-06-18 23:33 | 2026-06-18 23:33
IA-FM01-F01-TC01 | Successful Login by Active Instance Admin | 1. Account exists and is active. 2.Account is assigned admin previleges; | 1. Open Instance Portal URL 2. Enter valid email 3. Enter correct password 4. Click Login | User is authenticated successfully and redirected to the Instance Admin Dashboard | Ready for testing | Pass | Pending Recommendation |  | 2025-08-08 | In-progress | Pending Recommendation |  | 2025-10-05 | 2025-12-22
IA-FM01-F01-TC02 | Login with Incorrect Password | Valid instance admin account exists | 1. Open login page 2. Enter valid email 3. Enter incorrect password 4. Click Login | Login fails and an error message indicating invalid credentials is displayed | Ready for testing | Fail | Pending Recommendation | Fail - The Users page shows a populated table with name, email, role and status columns. did not behave as expected (runtime: Test timeout of 30000ms exceeded while running "beforeEach" hook.) | 2025-08-08 | In-progress | Pending Recommendation |  | 2025-10-05 | 2026-06-18 23:33 | 2026-06-18 23:33
IA-FM01-F01-TC03 | Login Attempt by Deactivated Instance Admin Account | Instance admin account is deactivated | 1. Deactivate admin account 2. Open Admin Portal 3. Enter credentials 4. Click Login | Login is denied and system displays account deactivation message | Not started | Fail | Pending Recommendation | Fail - Searching a term taken from the first row returned matching rows that contain that term. did not behave as expected (runtime: Test timeout of 30000ms exceeded while running "beforeEach" hook.) | 2025-08-08 | In-progress | Pending Recommendation |  | 2025-10-05 | 2026-06-18 23:33 | 2026-06-18 23:33
IA-FM01-F01-TC04 | Login Attempt by Non-admin User | User has a valid iSOKO account but is not an instance admin | 1. Open Instance Admin Portal login page 2. Enter valid credentials 3. Click Login | Access is denied and user is informed they do not have permission to access the portal | Not started | Fail | Pending Recommendation | Fail - No location/country filter control is present on the Users list in this build. (runtime: Test timeout of 30000ms exceeded while running "beforeEach" hook.) | 2025-08-08 | In-progress | Pending Recommendation |  | 2025-10-05 | 2026-06-18 23:33 | 2026-06-18 23:33
IA-FM01-F01-TC05 | Concurrent Login Handling | Same admin credentials available on two devices | 1. Log in on Device A 2. Log in on Device B using same credentials | System enforces session policy (either allows both sessions) | Not started | Fail | Pending Recommendation | Fail - No role filter control is present on the Users list in this build. (runtime: Test timeout of 30000ms exceeded while running "beforeEach" hook.) | 2025-08-08 | In-progress | Pending Recommendation |  | 2025-10-05 | 2026-06-18 23:33 | 2026-06-18 23:33
IA-FM01-F01-TC06 | Unauthorized Access to System Admin URLs | User is logged in as Association Admin | 1. Manually enter System Admin Portal URL | Access is denied and user is redirected to the login page | Not started | Fail | Pending Recommendation | Fail - No status filter control is present on the Users list in this build. (runtime: Test timeout of 30000ms exceeded while running "beforeEach" hook.) | 2025-08-08 | In-progress | Pending Recommendation |  |  | 2026-06-18 23:33 | 2026-06-18 23:33
Fail | [7 empty] | Fail - Opening a user via View navigated to the profile route and displayed identifying details (email, phone, role, status, name). did not behave as expected (runtime: Test timeout of 30000ms exceeded while running "beforeEach" hook.) | 2025-08-08 | In-progress | Pending Recommendation |  |  | 2026-06-18 23:33 | 2026-06-18 23:33
IA-AL01-F02-TC01 | Dashboard Metrics Load Correctly | Instance has users, content, orders and transactions | 1. Log in as instance admin portal 2. View dashboard metrics | Dashboard metrics display accurate data matching backend records | Ready for testing | Pending Testing | Pending Recommendation | Blocked - would mutate a real production user; no dedicated disposable test user available. | 2025-08-08 | In-progress | Pending Recommendation |  | 2025-10-05 | 2025-12-22
IA-AL01-F02-TC02 | View top rated items | View top rated association, sellers and products | 1. Perform an action (e.g. approve join request) 2. Navigate to dashboard | Top rated items are displayed on the dashboard | Not started | Fail | Pending Recommendation | Fail - On the user profile, phone and email have no enabled editor, confirming they are read-only as required. did not behave as expected (runtime: Test timeout of 30000ms exceeded while running "beforeEach" hook.) | 2025-08-08 | In-progress | Pending Recommendation |  | 2025-10-05 | 2026-06-18 23:33 | 2026-06-18 23:33
IA-AL01-F02-TC03 | Access to Authorized Sections | User role is Instance Admin | 1. Log in as instance admin 2. Access User Management, Orders, Referral Sharing | Access is granted to all instance level functions | Not started | Pending Testing | Pending Recommendation | Blocked - would mutate a real production user; no dedicated disposable test user available. | 2025-08-08 | In-progress | Pending Recommendation |  | 2025-10-05
Blocked - would mutate a real production user; no dedicated disposable test user available. | [12 empty] | 2025-10-05
IA-FM01-F15-TC01 | View User List | Admin user is logged in with user management permissions | 1. Navigate to Admin Portal → Users. 2. Load user listing page. | - List of users displayed.- Users show key attributes (name, email, role, country, status, association). | Not started | Pending Testing | Pending Recommendation | Blocked - would mutate a real production user; no dedicated disposable test user available. | 2025-08-08 | In-progress | Pending Recommendation |  | 2025-10-05
IA-FM01-F15-TC02 | Search User by Name or Email | User records exist in the system | 1. Navigate to user list. 2. Enter name or email in search field. 3. Submit search. | - Matching users returned.- No irrelevant users displayed. | Not started | Pending Testing | Pending Recommendation | Blocked - would mutate a real production user; no dedicated disposable test user available. | 2025-08-08 | In-progress | Pending Recommendation |  | 2025-10-05
IA-FM01-F15-TC03 | Filter Users by Location | Multiple locations configured | 1. Open user list. 2. Apply location filter. 3. Refresh results. | - Only users from selected country are displayed. | Not started | Pending Testing | Pending Recommendation |  | 2025-08-08 | In-progress | Pending Recommendation |  | 2025-10-05
IA-FM01-F15-TC04 | Filter Users by Role | Multiple user roles exist | 1. Open user list. 2. Apply role filter (Buyer, Seller, Admin, Association Admin, etc.). | - Users displayed match selected role. | Not started | Fail | Pending Recommendation | Fail - Created a throwaway role via Add Role and confirmed it appears in the roles table (cleaned up by deactivation afterwards). did not behave as expected (runtime: Test timeout of 30000ms exceeded while running "beforeEach" hook.) | 2025-08-08 | In-progress | Pending Recommendation |  | 2025-10-05 | 2026-06-18 23:33 | 2026-06-18 23:33
IA-FM01-F15-TC05 | Filter Users by Status | Users have different statuses | 1. Apply status filter (Active, Inactive, Suspended). | - Only users with selected status are shown. | Not started | Fail | Pending Recommendation | Fail - Submitting an empty role name was rejected: the modal stayed open / a validation error showed / no new row was added. did not behave as expected (runtime: Test timeout of 30000ms exceeded while running "beforeEach" hook.) | 2025-08-08 | In-progress | Pending Recommendation |  | 2025-10-05 | 2026-06-18 23:33 | 2026-06-18 23:33
IA-FM01-F15-TC06 | View User Profile Details | User exists | 1. Click on a user record. 2. Open user profile view. | - Full user profile displayed.- Includes personal details, business info, roles, associations, activity summary. | Not started | Fail | Pending Recommendation | Fail - Re-using an existing role name was prevented; no duplicate row was created. did not behave as expected (runtime: Test timeout of 30000ms exceeded while running "beforeEach" hook.) | 2025-08-08 | In-progress | Pending Recommendation |  | 2025-10-05 | 2026-06-18 23:33 | 2026-06-18 23:33
IA-FM01-F15-TC07 | Update User Profile Details | User exists | 1. Click on a user record. 2. Open user profile view. 3. Click on Edit button. 4. Edit details(name,location) | -User details update | Not started | Fail | Pending Recommendation | Fail - Renamed the role then reverted it; the updated name appeared in the table, confirming edits persist. did not behave as expected (runtime: Test timeout of 30000ms exceeded while running "beforeEach" hook.) | 2025-08-08 | In-progress | Pending Recommendation |  | 2025-10-05 | 2026-06-18 23:33 | 2026-06-18 23:33
IA-FM01-F15-TC08 | Restriction on User profile edits | User exists | 1. Click on a user record. 2. Open user profile view. 3. Click on Edit button. 4. Edit details(phone number, email) | System block editing of user's phone number and email | Not started | Fail | Pending Recommendation | Fail - Opened the role editor and confirmed the Role Name and Active fields are displayed. did not behave as expected (runtime: Test timeout of 30000ms exceeded while running "beforeEach" hook.) | 2025-08-08 | In-progress | Pending Recommendation |  | 2025-10-05 | 2026-06-18 23:33 | 2026-06-18 23:33
IA-FM01-F15-TC10 | Assign User Role | User exists | 1.Select User. 2.Change role. 3. Save changes. | - Role updated successfully.- Permissions updated immediately.- Change logged. | Not started | Fail | Pending Recommendation | Fail - Unchecked Active and saved; re-opening the role confirmed it now reads inactive. did not behave as expected (runtime: Test timeout of 30000ms exceeded while running "beforeEach" hook.) | 2025-08-08 | In-progress | Pending Recommendation |  | 2025-10-05 | 2026-06-18 23:33 | 2026-06-18 23:33
IA-FM01-F15-TC11 | Activate User Account | User status is inactive | 1. Select User. 2. Click Activate. | - User status changes to active.- User can log in.- Action logged. | Not started | Fail | Pending Recommendation | Fail - Re-checked Active and saved; re-opening the role confirmed it now reads active again. did not behave as expected (runtime: Test timeout of 30000ms exceeded while running "beforeEach" hook.) | 2025-08-08 | In-progress | Pending Recommendation |  | 2025-10-05 | 2026-06-18 23:33 | 2026-06-18 23:33
IA-FM01-F15-TC12 | Deactivate User Account | User status is active | 1. Select user. 2. Click Deactivate. | - User cannot log in.- Existing sessions terminated.- Status updated and logged. | Not started | Fail | Pending Recommendation | Fail - The role editor exposes only an Active toggle - no permission-assignment UI exists in this build. (runtime: Test timeout of 30000ms exceeded while running "beforeEach" hook.) | 2025-08-08 | In-progress | Pending Recommendation |  | 2025-10-05 | 2026-06-18 23:33 | 2026-06-18 23:33
IA-FM01-F15-TC13 | Bulk User Actions | Multiple users selected | 1. Select multiple users. 2. Perform bulk action (activate/deactivate). | - Action applied to all selected users.- Partial failures reported. | Not started | Fail | Pending Recommendation | Fail - The role editor exposes only an Active toggle - no permission-assignment UI exists in this build. (runtime: Test timeout of 30000ms exceeded while running "beforeEach" hook.) | 2025-08-08 | In-progress | Pending Recommendation |  | 2025-10-05 | 2026-06-18 23:33 | 2026-06-18 23:33
Fail - The role editor exposes only an Active toggle - no permission-assignment UI exists in this build. (runtime: Test timeout of 30000ms exceeded while running "beforeEach" hook.) | [13 empty] | 2026-06-18 23:33 | 2026-06-18 23:33
IA-FM01-F03-TC01 | Create New Role | Super Admin logged in | 1. Admin → IAM → Roles 2. Click Add Role 3. Enter role name, description, scope (global/country) 4. Save | Role created successfully | Not started | Fail | Pending Recommendation | Fail - The role editor exposes only an Active toggle - no permission-assignment UI exists in this build. (runtime: Test timeout of 30000ms exceeded while running "beforeEach" hook.) | 2025-08-08 | In-progress | Pending Recommendation |  | 2025-10-05 | 2026-06-18 23:33 | 2026-06-18 23:33
IA-FM01-F03-TC02 | Create Role with Missing Mandatory Fields | Super Admin logged in | 1. Attempt to save without role name | Validation error displayed | Not started | Pending Testing | Pending Recommendation | Blocked - requires an audit-log surface not exposed in the instance admin UI. | 2025-08-08 | In-progress | Pending Recommendation |  | 2025-10-05
IA-FM01-F03-TC03 | Create Duplicate Role | Role name exists | 1. Attempt to create role with same name | System prevents duplication | Not started | Pending Testing | Pending Recommendation | Blocked - would mutate a real production user; no dedicated disposable test user available. | 2025-08-08 | In-progress | Pending Recommendation |  | 2025-10-05
IA-FM01-F03-TC04 | Edit Role Details | Role exists | 1. Edit name/description 2. Save | Changes saved successfully | Not started | Pending Testing | Pending Recommendation | Blocked - would mutate a real production user; no dedicated disposable test user available. | 2025-08-08 | In-progress | Pending Recommendation |  | 2025-10-05
IA-FM01-F03-TC05 | View Role Details | Role exists | 1. Open role | All permissions and metadata visible | Not started | Pending Testing | Pending Recommendation | Blocked - would mutate a real production user; no dedicated disposable test user available. | 2025-08-08 | In-progress | Pending Recommendation |  | 2025-10-05
IA-FM01-F03-TC06 | Deactivate Role | Role active | 1. Click Deactivate | Role marked inactive | Not started | Pending Testing | Pending Recommendation | Blocked - requires a second device/session or restricted user; not automatable with a single primary admin. | 2025-08-08 | In-progress | Pending Recommendation |  | 2025-10-05
IA-FM01-F03-TC07 | Reactivate Role | Role inactive | 1. Click Activate | Role restored | Not started | Pending Testing | Pending Recommendation | Blocked - requires a second device/session or restricted user; not automatable with a single primary admin. | 2025-08-08 | In-progress | Pending Recommendation |  | 2025-10-05
IA-FM01-F03-TC08 | Assign Permission to Role | Role exists | 1. Open role 2. Select feature(e.g. Approve Orders) 3. Assign permission 4. Save | Permission assigned | Not started | Pending Testing | Pending Recommendation | Blocked - requires a second device/session or restricted user; not automatable with a single primary admin. | 2025-08-08 | In-progress | Pending Recommendation |  | 2025-10-05
IA-FM01-F03-TC09 | Assign Multiple Permissions | Role exists | 1. Select multiple permissions 2. Save | All permissions applied | Not started | Pending Testing | Pending Recommendation | Blocked - test data unavailable: no non-admin / second-role account provisioned (primary admin only). | 2025-08-08 | In-progress | Pending Recommendation |  | 2025-10-05
IA-FM01-F03-TC10 | Remove Permission | Role exists and has assigned permission | 1. Remove one or more permission | Role loses capability | Not started | Pending Testing | Pending Recommendation |  | 2025-08-08 | In-progress | Pending Recommendation |  | 2025-10-05
IA-FM01-F03-TC11 | Remove All Permissions | Role has permissions | 1. Remove all 2. Save | Role has no access | Not started | Fail | Pending Recommendation | Fail - Created a location level with no parent via Add Level and confirmed it appears in the list (cleaned up by deactivation afterwards). did not behave as expected (runtime: Error: expect(locator).toBeVisible() failed) | 2025-08-08 | In-progress | Pending Recommendation |  | 2025-10-05 | 2026-06-18 23:33 | 2026-06-18 23:33
IA-FM01-F03-TC12 | Permission Removal Audit | Permission removed | 1. View audit log | Change recorded | Not started | Fail | Pending Recommendation | Fail - Created a child location level linked to parent ID 1 and confirmed it appears in the list. did not behave as expected (runtime: Error: expect(locator).toBeVisible() failed) | 2025-08-08 | In-progress | Pending Recommendation |  | 2025-10-05 | 2026-06-18 23:33 | 2026-06-18 23:33
IA-FM01-F03-TC13 | Assign Role to User | User exists | 1. Assign role | Role applied | Not started | Fail | Pending Recommendation | Fail - Submitting a level with no name was rejected: the modal stayed open / a validation error showed / no new row was added. did not behave as expected (runtime: Error: expect(locator).toBeVisible() failed) | 2025-08-08 | In-progress | Pending Recommendation |  | 2025-10-05 | 2026-06-18 23:33 | 2026-06-18 23:33
IA-FM01-F03-TC14 | Change User Role | User has role | 1. Assign new role | Old role replaced | Not started | Fail | Pending Recommendation | Fail - Re-using an existing level name was prevented; no duplicate was created. did not behave as expected (runtime: Error: expect(locator).toBeVisible() failed) | 2025-08-08 | In-progress | Pending Recommendation |  | 2025-10-05 | 2026-06-18 23:33 | 2026-06-18 23:33
IA-FM01-F03-TC15 | Remove Role from User | User has role | 1. Remove role | User loses access | Not started | Fail | Pending Recommendation | Fail - Deactivated the temp level via the Active toggle and confirmed it reads unchecked on re-open. did not behave as expected (runtime: Error: expect(locator).toBeVisible() failed) | 2025-08-08 | In-progress | Pending Recommendation |  | 2025-10-05 | 2026-06-18 23:33 | 2026-06-18 23:33
IA-FM01-F03-TC16 | Immediate Permission Enforcement | Role updated | 1. User performs action | Access updated immediately | Not started | Fail | Pending Recommendation | Fail - Reactivated the temp level and confirmed the Active toggle reads checked on re-open. did not behave as expected (runtime: Error: expect(locator).toBeVisible() failed) | 2025-08-08 | In-progress | Pending Recommendation |  | 2025-10-05 | 2026-06-18 23:33 | 2026-06-18 23:33
IA-FM01-F03-TC17 | Session Refresh Permission Update | User logged in | 1. Update role 2. Refresh session | Permissions updated | Not started | Pending Testing | Pending Recommendation | Blocked - requires a level with linked locations to be set up and torn down reliably; high risk of orphaned config on live env. | 2025-08-08 | In-progress | Pending Recommendation |  | 2025-10-05
IA-FM01-F03-TC18 | Prevent Access After Permission Removal | Permission removed | 1. Attempt action | Access denied | Not started | Fail | Pending Recommendation | Fail - After a level is deactivated it still appears in the default Location Levels list; inactive entries are not hidden. (runtime: Error: expect(locator).toBeVisible() failed) | 2025-08-08 | In-progress | Pending Recommendation |  | 2025-10-05 | 2026-06-18 23:33 | 2026-06-18 23:33
IA-FM01-F03-TC19 | UI Menu Visibility Enforcement | Role applied | 1. Login as user | Only allowed menus visible | Not started | Fail | Pending Recommendation | Fail - Created a parent location with no parent and confirmed it appears in the locations table. did not behave as expected (runtime: Error: expect(locator).toBeVisible() failed) | 2025-08-08 | In-progress | Pending Recommendation |  | 2025-10-05 | 2026-06-18 23:33 | 2026-06-18 23:33
Fail | [7 empty] | Fail - Created a child location linked to parent ID 1 and confirmed it appears in the table. did not behave as expected (runtime: Error: expect(locator).toBeVisible() failed) | [5 empty] | 2026-06-18 23:33 | 2026-06-18 23:33
IA-FM01-F10-TC01 | Create location level with parent location level | Super Admin logged in | 1. Navigate to Admin → Locations → Location Levels 2. Click Add Location Level 3. Enter name = Country 4. Leave parent level empty 5. Save | level created successfully | Not started | Fail | Pending Recommendation | Fail - The location form uses a free-text Level ID with no options list, so exclusion of inactive levels cannot be enforced or verified. (runtime: Error: expect(locator).toBeVisible() failed) | 2025-08-08 | In-progress | Pending Recommendation |  | 2025-10-05 | 2026-06-18 23:33 | 2026-06-18 23:33
IA-FM01-F10-TC02 | Create Child Location Level | Parent location level exists | 1. Add Location Level 2. Enter name 3. Select Add Parent Level 4. Select location level 5.Save | Location level created and linked to parent location level | Not started | Fail | Pending Recommendation | Fail - Submitting a location with missing fields was rejected: the modal stayed open / a validation error showed / no new row was added. did not behave as expected (runtime: Test timeout of 30000ms exceeded while running "beforeEach" hook.) | 2025-08-08 | In-progress | Pending Recommendation |  | 2025-10-05 | 2026-06-18 23:33 | 2026-06-18 23:33
IA-FM01-F10-TC03 | Create Location Level Without Name | Admin logged in | 1. Leave name empty 2. Save | Validation error displayed | Not started | Fail | Pending Recommendation | Fail - Re-using an existing location name was prevented; no duplicate was created. did not behave as expected (runtime: Test timeout of 30000ms exceeded while running "beforeEach" hook.) | 2025-08-08 | In-progress | Pending Recommendation |  | 2025-10-05 | 2026-06-18 23:33 | 2026-06-18 23:33
IA-FM01-F10-TC04 | Create Duplicate Location Level | Level exists | 1. Create level with same name | Duplicate prevented | Not started | Fail | Pending Recommendation | Fail - Set the location's Parent ID then reverted it; the update saved without error. did not behave as expected (runtime: Test timeout of 30000ms exceeded while running "beforeEach" hook.) | 2025-08-08 | In-progress | Pending Recommendation |  | 2025-10-05 | 2026-06-18 23:33 | 2026-06-18 23:33
IA-FM01-F10-TC05 | Deactivate Location Level | Level active | 1. Click Deactivate | Level marked inactive | Not started | Fail | Pending Recommendation | Fail - Deactivated the temp location via the Active toggle and saved. did not behave as expected (runtime: Test timeout of 30000ms exceeded while running "beforeEach" hook.) | 2025-08-08 | In-progress | Pending Recommendation |  | 2025-10-05 | 2026-06-18 23:33 | 2026-06-18 23:33
IA-FM01-F10-TC06 | Activate Location Level | Level inactive | 1. Click Activate | Level reactivated | Not started | Fail | Pending Recommendation | Fail - Reactivated the temp location and confirmed the Active toggle reads checked on re-open. did not behave as expected (runtime: Test timeout of 30000ms exceeded while running "beforeEach" hook.) | 2025-08-08 | In-progress | Pending Recommendation |  | 2025-10-05 | 2026-06-18 23:33 | 2026-06-18 23:33
IA-FM01-F10-TC07 | Prevent Deactivation if Locations Exist | Locations linked | 1. Attempt deactivation | System blocks or warns | Not started | Pending Testing | Pending Recommendation | Blocked - cross-feature dependency (user/product assignment) on live data; verified indirectly by TC11. | 2025-08-08 | In-progress | Pending Recommendation |  | 2025-10-05
IA-FM01-F10-TC08 | Visibility of Inactive Levels | Levels exist | 1. View list | Inactive not visible | Not started | Pending Testing | Pending Recommendation |  | 2025-08-08 | In-progress | Pending Recommendation |  | 2025-10-05
IA-FM01-F10-TC09 | Create Parent Location(without Parent location) | Location level exist and active | 1. Add Location 2. Select Level 3. Name 4. Save | Location created | Not started | Fail | Pending Recommendation | Fail - No export/download control is present on the Users list in this build. (runtime: Error: expect(locator).toBeVisible() failed) | 2025-08-08 | In-progress | Pending Recommendation |  | 2025-10-05 | 2026-06-18 23:33 | 2026-06-18 23:33
IA-FM01-F10-TC10 | Create child | Parent location exist Child location level exist | 1. Add Location 2. Enter name 3. Select location level 4. Select parent location 5. Save | Location created and linked to the parent location | Not started | Pending Testing | Pending Recommendation | Blocked - needs a specific pre-seeded data condition (e.g. 10,000+ rows) not present in the live environment. | 2025-08-08 | In-progress | Pending Recommendation |  | 2025-10-05
IA-FM01-F10-TC11 | Create Location Under Inactive Level | Level inactive | 1. Attempt creation | Location level not listed on options | Not started | Fail | Pending Recommendation | Fail - No export/download control is present on the Users list in this build, so the file name cannot be checked. (runtime: Error: expect(locator).toBeVisible() failed) | 2025-08-08 | In-progress | Pending Recommendation |  | 2025-10-05 | 2026-06-18 23:33 | 2026-06-18 23:33
IA-FM01-F10-TC12 | Create Location with Missing Fields | Admin logged in | 1. Leave name empty | Validation error | Not started | Fail | Pending Recommendation | Fail - No export/download control is present on the Users list in this build, so no file can be produced or opened. (runtime: Error: expect(locator).toBeVisible() failed) | 2025-08-08 | In-progress | Pending Recommendation |  | 2025-10-05 | 2026-06-18 23:33 | 2026-06-18 23:33
IA-FM01-F10-TC13 | Create Duplicate Location | Location exists | 1. Create with same name | Duplicate prevented | Not started | Fail | Pending Recommendation | Fail - No export/download control is present on the Users list in this build, so no exported header row exists to validate. (runtime: Error: expect(locator).toBeVisible() failed) | 2025-08-08 | In-progress | Pending Recommendation |  | 2025-10-05 | 2026-06-18 23:33 | 2026-06-18 23:33
IA-FM01-F10-TC14 | Change Parent Location | Location exists | 1. Edit location 2. Change parent | Parent updated | Not started | Fail | Pending Recommendation | Fail - No export/download control is present on the Users list in this build, so exported counts cannot be compared. (runtime: Error: expect(locator).toBeVisible() failed) | 2025-08-08 | In-progress | Pending Recommendation |  | 2025-10-05 | 2026-06-18 23:33 | 2026-06-18 23:33
IA-FM01-F10-TC15 | Deactivate Location | Location active | 1. Click Deactivate | Location inactive | Not started | Fail | Pending Recommendation | Fail - No export/download control is present on the Users list in this build, so exported data formatting cannot be checked. (runtime: Error: expect(locator).toBeVisible() failed) | 2025-08-08 | In-progress | Pending Recommendation |  | 2025-10-05 | 2026-06-18 23:33 | 2026-06-18 23:33
IA-FM01-F10-TC16 | Activate Location | Location inactive | 1. Click Activate | Location active | Not started | Fail | Pending Recommendation | Fail - No export/download control (nor a location/country filter) is present on the Users list in this build. (runtime: Error: expect(locator).toBeVisible() failed) | 2025-08-08 | In-progress | Pending Recommendation |  | 2025-10-05 | 2026-06-18 23:33 | 2026-06-18 23:33
IA-FM01-F10-TC17 | Prevent Use of Inactive Location | Location inactive | 1. Try assigning to user/product | Not visible | Not started | Fail | Pending Recommendation | Fail - No export/download control (nor an association filter) is present on the Users list in this build. (runtime: Error: expect(locator).toBeVisible() failed) | 2025-08-08 | In-progress | Pending Recommendation |  | 2025-10-05 | 2026-06-18 23:33 | 2026-06-18 23:33
Fail | [7 empty] | Fail - No export/download control (nor a role filter) is present on the Users list in this build. (runtime: Error: expect(locator).toBeVisible() failed) | 2025-08-08 | In-progress | Pending Recommendation |  | 2025-10-05 | 2026-06-18 23:33 | 2026-06-18 23:33
IA-FM01-F15-TC14 | Export All Users | Users exist | 1. No filters applied 2. Click Export (XLS) | All users exported | Not started | Fail | Pending Recommendation | Fail - No export/download control (nor a status filter) is present on the Users list in this build. (runtime: Error: expect(locator).toBeVisible() failed) | 2025-08-08 | In-progress | Pending Recommendation |  | 2025-10-05 | 2026-06-18 23:33 | 2026-06-18 23:33
IA-FM01-F15-TC15 | Export with Large User Volume | 10,000+ users | 1. Export full list | File generated without timeout | Not started | Fail | Pending Recommendation | Fail - No export/download control (nor a date-range filter) is present on the Users list in this build. (runtime: Error: expect(locator).toBeVisible() failed) | 2025-08-08 | In-progress | Pending Recommendation |  | 2025-10-05 | 2026-06-18 23:33 | 2026-06-18 23:33
IA-FM01-F15-TC16 | File Naming Convention | Export initiated | 1. Download file | Name includes date/time | Not started | Fail | Pending Recommendation | Fail - No export/download control (nor filter controls) is present on the Users list in this build. (runtime: Error: expect(locator).toBeVisible() failed) | 2025-08-08 | In-progress | Pending Recommendation |  | 2025-10-05 | 2026-06-18 23:33 | 2026-06-18 23:33
IA-FM01-F15-TC17 | XLS File Opens Correctly | Export completed | 1. Open file | No corruption | Not started | Fail | Pending Recommendation | Fail - No export/download control is present on the Users list in this build, so an empty-result export cannot be exercised. (runtime: Error: expect(locator).toBeVisible() failed) | 2025-08-08 | In-progress | Pending Recommendation |  | 2025-10-05 | 2026-06-18 23:33 | 2026-06-18 23:33
IA-FM01-F15-TC18 | Header Row Validation | XLS opened | 1. Check headers | Correct column names | Not started | Pending Testing | Pending Recommendation |  | 2025-08-08 | In-progress | Pending Recommendation |  | 2025-10-05
IA-FM01-F15-TC19 | User Count Validation | Users exist | 1. Compare UI count vs XLS rows | Counts match | Not started | Pass | Pending Recommendation | Pass - The Associations Management page shows a populated table with association, country, status and member columns. | 2025-08-08 | In-progress | Pending Recommendation |  | 2025-10-05 | 2026-06-18 23:33 | 2026-06-18 23:33
IA-FM01-F15-TC20 | Data Formatting Validation | Mixed data | 1. Review fields | Correct data types | Not started | Pass | Pending Recommendation | Pass - Searching a term taken from the first row returned results that contain that term. | 2025-08-08 | In-progress | Pending Recommendation |  | 2025-10-05 | 2026-06-18 23:33 | 2026-06-18 23:33
IA-FM01-F15-TC21 | Export Filtered by Location | Users in multiple locations | 1. Filter by location 2. Export | Only selected country users | Not started | Pass | Pending Recommendation | Pass - automated check passed against the live portal. | 2025-08-08 | In-progress | Pending Recommendation |  | 2025-10-05 | 2026-06-18 23:33 | 2026-06-18 23:33
IA-FM01-F15-TC22 | Export Filtered by Association | Associations exist | 1. Filter by association 2. Export | Correct subset exported | Not started | Pass | Pending Recommendation | Pass - Switched the status tabs (Approved, then back to Pending Review) and the table re-rendered for each. | 2025-08-08 | In-progress | Pending Recommendation |  | 2025-10-05 | 2026-06-18 23:33 | 2026-06-18 23:33
IA-FM01-F15-TC23 | Export Filtered by Role | Multiple roles exist | 1. Filter by role 2. Export | Role-specific users exported | Not started | Pass | Pending Recommendation | Pass - Opened a pending application's details (code, country, members, status, email); Approve/Decline/Request Info actions are available (not clicked). | 2025-08-08 | In-progress | Pending Recommendation |  | 2025-10-05 | 2026-06-18 23:33 | 2026-06-18 23:33
IA-FM01-F15-TC24 | Export Filtered by Status | Active & inactive users exist | 1. Filter status 2. Export | Only matching users | Not started | Pending Testing | Pending Recommendation | Blocked - irreversible / notification-sending action on live data (excluded by semi-destructive scope). | 2025-08-08 | In-progress | Pending Recommendation |  | 2025-10-05
IA-FM01-F15-TC25 | Export Filtered by Date Range | Registration dates exist | 1. Apply date filter 2. Export | Correct subset exported | Not started | Pending Testing | Pending Recommendation | Blocked - irreversible / notification-sending action on live data (excluded by semi-destructive scope). | 2025-08-08 | In-progress | Pending Recommendation |  | 2025-10-05
IA-FM01-F15-TC26 | Export with Multiple Filters | Filters applied | 1. Apply multiple filters 2. Export | All conditions respected | Not started | Pending Testing | Pending Recommendation | Blocked - irreversible / notification-sending action on live data (excluded by semi-destructive scope). | 2025-08-08 | In-progress | Pending Recommendation |  | 2025-10-05
IA-FM01-F15-TC27 | Export Empty Result Set | No matching users | 1. Apply filter 2. Export | Empty file or warning | Not started | Pass | Pending Recommendation | Pass - Opened an approved association profile and confirmed profile details (code, country, founded, members, email, address). | 2025-08-08 | In-progress | Pending Recommendation |  | 2025-10-05 | 2026-06-18 23:33 | 2026-06-18 23:33
ASSOCIATION MANAGEMENT | [5 empty] | Pending Testing |  | Blocked - mutates a real association profile; no disposable association available (excluded by semi-destructive scope). |  |  |  |  | 2025-10-05
IA-CM05-F01-TC01 | View Associations List | Admin user logged in with association management permissions | 1. Navigate to Admin Portal → Associations. 2. Load associations listing page. | - List of all registered associations displayed.- Key details shown (name, country, status, number of members, admin). | Not started | Pass | Pending Recommendation | Pass - Opened an association profile and confirmed a members section/list is present. | 2025-08-08 | In-progress | Pending Recommendation |  | 2025-10-05 | 2026-06-18 23:33 | 2026-06-18 23:33
IA-CM05-F01-TC02 | Search Association | Associations exist | 1. Enter association name or keyword in search field. 2. Submit search. | - Matching associations returned accurately. | Not started | Pending Testing | Pending Recommendation | Blocked - irreversible / notification-sending action on live data (excluded by semi-destructive scope). | 2025-08-08 | In-progress | Pending Recommendation |  | 2025-10-05
IA-CM05-F01-TC03 | Filter Associations by Location | Multiple Location configured | 1. Apply country filter. 2. Refresh list. | - Only associations from selected country displayed. | Not started | Pending Testing | Pending Recommendation | Blocked - irreversible / notification-sending action on live data (excluded by semi-destructive scope). | 2025-08-08 | In-progress | Pending Recommendation |  | 2025-10-05
IA-CM05-F01-TC04 | Filter Associations by Status | Associations have different statuses | 1. Apply status filter (Pending, Approved, Suspended, Rejected). | - Associations displayed match selected status. | Not started | Pending Testing | Pending Recommendation | Blocked - irreversible / notification-sending action on live data (excluded by semi-destructive scope). | 2025-08-08 | In-progress | Pending Recommendation |  | 2025-10-05
IA-CM05-F01-TC05 | Review Association Registration Application | Association application submitted | 1. Open pending association application. 2. Review submitted details and documents. | - Full application details visible.- Documents accessible for review. | Not started | Fail | Pending Recommendation | Fail - No association marketplace view is exposed in the instance admin portal. (runtime: Error: No marketplace view is exposed in the instance admin portal) | 2025-08-08 | In-progress | Pending Recommendation |  | 2025-10-05 | 2026-06-18 23:33 | 2026-06-18 23:33
IA-CM05-F01-TC06 | Approve Association Registration | Pending association application exists | 1. Review application. 2. Click Approve. 3. Confirm action. | - Association status updated to Approved.- Association admin notified.- Association becomes visible on platform. | Not started | Pending Testing | Pending Recommendation |  | 2025-08-08 | In-progress | Pending Recommendation |  | 2025-10-05
IA-CM05-F01-TC07 | Reject Association Registration | Pending association application exists | 1. Review application. 2. Click Reject. 3. Provide rejection reason. | - Application rejected.- Reason recorded.- Applicant notified. | Not started | Fail | Pending Recommendation | Fail - Orders page renders; filtering to Pending shows the orders table with order/status/date/total columns. did not behave as expected (runtime: Test timeout of 30000ms exceeded while running "beforeEach" hook.) | 2025-08-08 | In-progress | Pending Recommendation |  | 2025-10-05 | 2026-06-18 23:33 | 2026-06-18 23:33
IA-CM05-F01-TC08 | Request Additional Information | Pending application exists | 1. Open application. 2. Click Request More Info. 3. Enter required details. | - Application marked as Pending Info.- Notification sent to applicant. | Not started | Fail | Pending Recommendation | Fail - Opened an order via View and confirmed the detail page shows product, quantity, price and total. did not behave as expected (runtime: Test timeout of 30000ms exceeded while running "beforeEach" hook.) | 2025-08-08 | In-progress | Pending Recommendation |  | 2025-10-05 | 2026-06-18 23:33 | 2026-06-18 23:33
IA-CM05-F01-TC10 | View Association Profile | Association exists | 1. Open association profile. | - Profile details displayed (description, sector, location, admins, members). | Not started | Fail | Pending Recommendation | Fail - The Pending filter lists orders whose status reads Pending, confirming the default status. did not behave as expected (runtime: Test timeout of 30000ms exceeded while running "beforeEach" hook.) | 2025-08-08 | In-progress | Pending Recommendation |  | 2025-10-05 | 2026-06-18 23:33 | 2026-06-18 23:33
IA-CM05-F01-TC11 | Edit association details | Association exists | 1. Open association profile. 2. Click on edit 3. Save changes. | - Changes saved | Not started | Pending Testing | Pending Recommendation | Blocked - order state transitions / buyer-seller actions mutate live orders and notify real users (excluded by semi-destructive scope). | 2025-08-08 | In-progress | Pending Recommendation |  | 2025-10-05
IA-CM05-F01-TC12 | Monitor Association Members | Association has members | 1. Open association members tab. | - List of members displayed with status. | Not started | Pending Testing | Pending Recommendation | Blocked - order state transitions / buyer-seller actions mutate live orders and notify real users (excluded by semi-destructive scope). | 2025-08-08 | In-progress | Pending Recommendation |  | 2025-10-05
IA-CM05-F01-TC13 | Remove Member from Association (Admin Override) | Member exists in association | 1. Select member. 2. Click Remove Member. 3. Confirm action. | - Member removed from association. - Member retains iSOKO account. - Action logged. | Not started | Pending Testing | Pending Recommendation | Blocked - order state transitions / buyer-seller actions mutate live orders and notify real users (excluded by semi-destructive scope). | 2025-08-08 | In-progress | Pending Recommendation |  | 2025-10-05
IA-CM05-F01-TC14 | Suspend Association | Association approved and active | 1. Open association profile. 2. Click Suspend. 3. Provide suspension reason. | - Association status changed to Suspended. - Marketplace visibility disabled. - Association admin notified. | Not started | Pending Testing | Pending Recommendation | Blocked - order state transitions / buyer-seller actions mutate live orders and notify real users (excluded by semi-destructive scope). | 2025-08-08 | In-progress | Pending Recommendation |  | 2025-10-06
IA-CM05-F01-TC15 | Reinstate Suspended Association | Association suspended | 1. Open association profile. 2. Click Reinstate. | - Association restored to active status. - Marketplace visibility re-enabled. | Not started | Pending Testing | Pending Recommendation | Blocked - order state transitions / buyer-seller actions mutate live orders and notify real users (excluded by semi-destructive scope). | 2025-08-08 | In-progress | Pending Recommendation |  | 2025-10-05
IA-CM05-F01-TC16 | Verify Association Marketplace Page | Association approved | 1. Open marketplace view. 2. Navigate to association page. | - Association marketplace page visible. - Member listings aggregated correctly. | Not started | Pending Testing | Pending Recommendation | Blocked - order state transitions / buyer-seller actions mutate live orders and notify real users (excluded by semi-destructive scope). | 2025-08-08 | In-progress | Pending Recommendation |  | 2025-10-05
[6 empty] | Pending Testing |  | Blocked - order state transitions / buyer-seller actions mutate live orders and notify real users (excluded by semi-destructive scope).
[6 empty] | Pending Testing |  | Blocked - order state transitions / buyer-seller actions mutate live orders and notify real users (excluded by semi-destructive scope).
PRODUCT CATEGORY, SUB-CATEGORY AND COMMODITY | [5 empty] | Pending Testing |  | Blocked - order state transitions / buyer-seller actions mutate live orders and notify real users (excluded by semi-destructive scope). | 2025-08-08 | In-progress | Pending Recommendation |  | 2025-10-07
IA-CM02-F11-TC01 | Create New Category | Admin logged in with marketplace permissions | 1. Navigate to Admin → Marketplace → Categories 2. Click Add Category 3. Enter category name, description, icon/image 4. Save | Category created successfully and listed as Active | Not started | Pending Testing | Pending Recommendation | Blocked - order state transitions / buyer-seller actions mutate live orders and notify real users (excluded by semi-destructive scope). | 2025-08-08 | In-progress | Pending Recommendation |  | 2025-10-10
IA-CM02-F11-TC02 | Create Category with Missing Mandatory Fields | Admin logged in | 1. Click Add Category 2. Leave name empty 3. Save | Validation error shown; category not created | Not started | Pending Testing | Pending Recommendation | Blocked - order state transitions / buyer-seller actions mutate live orders and notify real users (excluded by semi-destructive scope). | 2025-08-08 | In-progress | Pending Recommendation |  | 2025-10-11
IA-CM02-F11-TC03 | Create Duplicate Category | Category with same name exists | 1. Add category using existing name 2. Save | System prevents duplication or prompts admin | Not started | Pending Testing | Pending Recommendation | Blocked - order state transitions / buyer-seller actions mutate live orders and notify real users (excluded by semi-destructive scope). | 2025-08-08 | In-progress | Pending Recommendation |  | 2025-10-12
IA-CM02-F11-TC04 | Edit Existing Category | Category exists | 1. Select category 2. Edit name/description/icon 3. Save | Category updated successfully | Not started | Pending Testing | Pending Recommendation | Blocked - order state transitions / buyer-seller actions mutate live orders and notify real users (excluded by semi-destructive scope). | 2025-08-08 | In-progress | Pending Recommendation |  | 2025-10-13
IA-CM02-F11-TC05 | Deactivate Category | Category is active | 1. Select category 2. Click Deactivate 3. Confirm | Category status set to Inactive, removed from the frontend | Not started | Pending Testing | Pending Recommendation | Blocked - order state transitions / buyer-seller actions mutate live orders and notify real users (excluded by semi-destructive scope). | 2025-08-08 | In-progress | Pending Recommendation |  | 2025-10-14
IA-CM02-F11-TC06 | Verify Deactivated Category Visibility | Category deactivated | 1. Open marketplace filters as user | Category not visible/selectable | Not started | Pending Testing | Pending Recommendation | Blocked - order state transitions / buyer-seller actions mutate live orders and notify real users (excluded by semi-destructive scope). | 2025-08-08 | In-progress | Pending Recommendation |  | 2025-10-15
IA-CM02-F11-TC07 | Reactivate Category | Category inactive | 1. Select inactive category 2. Click Activate | Category becomes active and visible | Not started | Pending Testing | Pending Recommendation | Blocked - order state transitions / buyer-seller actions mutate live orders and notify real users (excluded by semi-destructive scope). | 2025-08-08 | In-progress | Pending Recommendation |  | 2025-10-16
IA-CM02-F11-TC08 | Create Subcategory under Category | Category active | 1. Open category 2. Click Add Subcategory 3. Enter details 4. Save | Subcategory created and linked to parent category | Not started | Pending Testing | Pending Recommendation |  | 2025-08-08 | In-progress | Pending Recommendation |  | 2025-10-18
IA-CM02-F11-TC09 | Create Subcategory under Inactive Category | Category inactive | 1. Attempt to add subcategory | System blocks action | Not started | Fail | Pending Recommendation | Fail - No Email/SMS template configuration section is exposed in the instance admin portal navigation. (runtime: Test timeout of 30000ms exceeded while running "beforeEach" hook.) | 2025-08-08 | In-progress | Pending Recommendation |  | 2025-10-19 | 2026-06-18 23:33 | 2026-06-18 23:33
IA-CM02-F11-TC10 | Edit Subcategory | Subcategory exists | 1. Select subcategory 2. Edit details 3. Save | Changes saved successfully | Not started | Pending Testing | Pending Recommendation | Blocked - editing live email/SMS templates affects production notifications (excluded by semi-destructive scope). | 2025-08-08 | In-progress | Pending Recommendation |  | 2025-10-20
IA-CM02-F11-TC11 | Deactivate Subcategory | Subcategory active | 1. Select subcategory 2. Click Deactivate | Subcategory becomes inactive | Not started | Pending Testing | Pending Recommendation | Blocked - editing live email/SMS templates affects production notifications (excluded by semi-destructive scope). | 2025-08-08 | In-progress | Pending Recommendation |  | 2025-10-21
IA-CM02-F11-TC12 | Verify Product Visibility after Subcategory Deactivation | Products exist under subcategory | 1. Deactivate subcategory 2. View marketplace | Sub category unlisted | Not started | Pending Testing | Pending Recommendation | Blocked - editing live email/SMS templates affects production notifications (excluded by semi-destructive scope). | 2025-08-08 | In-progress | Pending Recommendation |  | 2025-10-22
IA-CM02-F11-TC13 | Reactivate Subcategory | Subcategory inactive | 1. Activate subcategory | Subcategory visible again on the frontend | Not started | Pending Testing | Pending Recommendation | Blocked - editing live email/SMS templates affects production notifications (excluded by semi-destructive scope). | 2025-08-08 | In-progress | Pending Recommendation |  | 2025-10-23
IA-CM02-F11-TC14 | Create Commodity under Subcategory | Category & subcategory active | 1. Open subcategory 2. Click Add Commodity 3. Enter name, unit, description 4. Save | Commodity created successfully | Not started | Pending Testing | Pending Recommendation | Blocked - editing live email/SMS templates affects production notifications (excluded by semi-destructive scope). | 2025-08-08 | In-progress | Pending Recommendation |  | 2025-10-25
IA-CM02-F11-TC15 | Create Commodity under Inactive Subcategory | Subcategory inactive | 1. Attempt to add commodity | System blocks creation | Not started | Pending Testing | Pending Recommendation | Blocked - editing live email/SMS templates affects production notifications (excluded by semi-destructive scope). | 2025-08-08 | In-progress | Pending Recommendation |  | 2025-10-26
IA-CM02-F11-TC16 | Edit Commodity Details | Commodity exists | 1. Select commodity 2. Edit details 3. Save | Commodity updated | Not started | Pending Testing | Pending Recommendation | Blocked - editing live email/SMS templates affects production notifications (excluded by semi-destructive scope). | 2025-08-08 | In-progress | Pending Recommendation |  | 2025-10-27
IA-CM02-F11-TC17 | Deactivate Commodity | Commodity active | 1. Select commodity 2. Click Deactivate | Commodity becomes inactive | Not started | Pending Testing | Not started | Blocked - editing live email/SMS templates affects production notifications (excluded by semi-destructive scope). | 2025-08-08 | In-progress | Pending Recommendation |  | 2025-10-28
IA-CM02-F11-TC18 | Verify Product Creation Restriction | Commodity inactive | 1. Attempt to list product using commodity | Commodity not selectable | Not started | Pending Testing | Pending Recommendation | Blocked - editing live email/SMS templates affects production notifications (excluded by semi-destructive scope). | 2025-08-08 | In-progress | Pending Recommendation |  | 2025-10-29
IA-CM02-F11-TC19 | Reactivate Commodity | Commodity inactive | 1. Activate commodity | Commodity available for listing | Not started | Pending Testing | Pending Recommendation | Blocked - editing live email/SMS templates affects production notifications (excluded by semi-destructive scope). | 2025-08-08 | In-progress | Pending Recommendation |  | 2025-10-30
IA-CM02-F11-TC20 | Validate Hierarchical Filtering | Categories exist | 1. Select category → subcategory → commodity | Correct hierarchical filtering applied | Not started | Pending Testing | Pending Recommendation | Blocked - editing live email/SMS templates affects production notifications (excluded by semi-destructive scope). | 2025-08-08 | In-progress | Pending Recommendation |  | 2025-10-31
Blocked - editing live email/SMS templates affects production notifications (excluded by semi-destructive scope). | [9 empty] | In-progress | Pending Recommendation |  | 2025-11-01
IA-CM02-F12-TC01 | Create Service Category | Admin logged in | 1. Admin → Services → Categories 2. Click Add Category 3. Enter details 4. Save | Category created | Not started | Pending Testing | Pending Recommendation | Blocked - editing live email/SMS templates affects production notifications (excluded by semi-destructive scope). | 2025-08-08 | In-progress | Pending Recommendation |  | 2025-11-03
IA-CM02-F12-TC02 | Create Service Category with Missing Fields | Admin logged in | 1. Save without name | Validation error | Not started | Pending Testing | Pending Recommendation | Blocked - editing live email/SMS templates affects production notifications (excluded by semi-destructive scope). | 2025-08-08 | In-progress | Pending Recommendation |  | 2025-11-04
IA-CM02-F12-TC03 | Edit Service Category | Category exists | 1. Edit details 2. Save | Category updated | Not started | Pending Testing | Pending Recommendation | Blocked - editing live email/SMS templates affects production notifications (excluded by semi-destructive scope). | 2025-08-08 | In-progress | Pending Recommendation |  | 2025-11-05
IA-CM02-F12-TC04 | Deactivate Service Category | Category active | 1. Click Deactivate | Category becomes inactive | Not started | Pending Testing | Pending Recommendation |  | 2025-08-08 | In-progress | Pending Recommendation |  | 2025-11-06
IA-CM02-F12-TC05 | Prevent Listing under Inactive Category | Category inactive | 1. Try to create service | Category not selectable | Not started | Pending Testing | Pending Recommendation |  | 2025-08-08 | In-progress | Pending Recommendation |  | 2025-11-07
IA-CM02-F12-TC06 | Reactivate Service Category | Category inactive | 1. Activate category | Category visible again | Not started | Pending Testing | Pending Recommendation |  | 2025-08-08 | In-progress | Pending Recommendation |  | 2025-11-08
IA-CM02-F12-TC07 | Create Service Type (Sub-category) | Category active | 1. Open category 2. Click Add Service Type 3. Save | Service type created | Not started | Pending Testing | Pending Recommendation |  | 2025-08-08 | In-progress | Pending Recommendation |  | 2025-11-09
IA-CM02-F12-TC08 | Edit Service Type | Service type exists | 1. Edit details 2. Save | Changes saved | Not started | Pending Testing | Pending Recommendation |  | 2025-08-08 | In-progress | Pending Recommendation |  | 2025-11-12
IA-CM02-F12-TC09 | Deactivate Service Type | Service type active | 1. Deactivate | Service type inactive | Not started | Pending Testing | Pending Recommendation |  | 2025-08-08 | In-progress | Pending Recommendation |  | 2025-11-13
IA-CM02-F12-TC10 | Reactivate Service Type | Service type inactive | 1. Activate | Service type active | Not started | Pending Testing | Pending Recommendation |  | 2025-08-08 | In-progress | Pending Recommendation |  | 2025-11-14
IA-CM02-F12-TC11 | List a service under deactivate service type | Service type inactive | 1. List a service | Service type not visible | Not started | Pending Testing | Pending Recommendation |  | 2025-08-08 | In-progress | Pending Recommendation |  | 2025-11-20
MEASUREMENT UNIT AND METRICS
IA-CM02-F13-TC01 | Create Measurement Metric | Admin logged in with configuration permissions | 1. Navigate to Admin → Marketplace Settings → Measurement Metrics 2. Click Add Metric 3. Enter metric details 4. Save | Metric created successfully and listed as Active | Not started | Pending Testing | Pending Recommendation |  | 2025-08-08 | In-progress | Pending Recommendation |  | 2025-11-24
IA-CM02-F13-TC02 | Create Metric with Missing Mandatory Fields | Admin logged in | 1. Attempt to save metric without name | Validation error displayed; metric not created | Not started | Pending Testing | Pending Recommendation |  | 2025-08-08 | In-progress | Pending Recommendation |  | 2025-11-25
IA-CM02-F13-TC03 | Create Duplicate Metric | Metric with same name exists | 1. Attempt to create metric with same name | System blocks duplicate or prompts admin | Not started | Pending Testing | Pending Recommendation |  | 2025-08-08 | In-progress | Pending Recommendation |  | 2025-11-26
IA-CM02-F13-TC04 | Edit Measurement Metric | Metric exists | 1. Select metric 2. Edit name/description 3. Save | Metric updated successfully | Not started | Pending Testing | Pending Recommendation |  | 2025-08-09 | In-progress | Pending Recommendation |  | 2025-11-26
IA-CM02-F13-TC05 | Deactivate Measurement Metric | Metric active | 1. Select metric 2. Click Deactivate 3. Confirm | Metric status changes to Inactive | Not started | Pending Testing | Pending Recommendation |  | 2025-08-10 | In-progress | Pending Recommendation |  | 2025-11-26
IA-CM02-F13-TC06 | Verify Inactive Metric Not Selectable | Metric inactive | 1. Attempt to measurement unit | Metric not available for selection | Not started | Pending Testing | Pending Recommendation |  | 2025-08-11 | In-progress | Pending Recommendation |  | 2025-11-26
IA-CM02-F13-TC07 | Reactivate Measurement Metric | Metric inactive | 1. Click Activate | Metric restored to active status | Not started | Pending Testing | Pending Recommendation |  | 2025-08-12 | In-progress | Pending Recommendation |  | 2025-11-26
IA-CM02-F13-TC08 | Create Measurement Unit | Admin logged in with configuration permissions | 1. Navigate to Admin → Marketplace Settings → Measurement Units 2. Click Add Unit 3. Enter metric details 4. Save | Unit created successfully and listed as Active | Not started | Pending Testing | Pending Recommendation |  | 2025-08-12 | In-progress | Pending Recommendation |  | 2025-11-26
IA-CM02-F13-TC09 | Create UNit with Missing Mandatory Fields | Admin logged in | 1. Attempt to save Unit without name | Validation error displayed; unit not created | Not started | Pending Testing | Pending Recommendation |  | 2025-08-12 | In-progress | Pending Recommendation |  | 2025-11-26
IA-CM02-F13-TC10 | Create Duplicate Unit | Unit with same name exists | 1. Attempt to create Unit with same name | System blocks duplicate or prompts admin | Not started | Pending Testing | Pending Recommendation |  | 2025-08-12 | In-progress | Pending Recommendation |  | 2025-11-26
IA-CM02-F13-TC11 | Edit Measurement Unit | Unit exists | 1. Select Unit 2. Edit name/description 3. Save | Unit updated successfully | Not started | Pending Testing | Pending Recommendation |  | 2025-08-12 | In-progress | Pending Recommendation |  | 2025-11-26
IA-CM02-F13-TC12 | Deactivate Measurement Unit | Unit active | 1. Select Unit 2. Click Deactivate 3. Confirm | Unit status changes to Inactive | Not started | Pending Testing | Pending Recommendation |  | 2025-08-12 | In-progress | Pending Recommendation |  | 2025-11-26
IA-CM02-F13-TC13 | Verify Inactive Unit Not Selectable | Metric inactive | 1. Attempt to create a marketplace product/service | Unit not available for selection | Not started | Pending Testing | Pending Recommendation |  | 2025-08-12 | In-progress | Pending Recommendation |  | 2025-11-26
IA-CM02-F13-TC14 | Reactivate Measurement Metric | Metric inactive | 1. Click Activate | Metric restored to active status | Not started | Pending Testing | Pending Recommendation |  | 2025-08-12 | In-progress | Pending Recommendation |  | 2025-11-26
ADMIN PRODUCT LISTING | [9 empty] | In-progress | Pending Recommendation |  | 2025-11-26
IA-CM02-F09-TC01 | Approve Product Listing | Listing in Pending Approval | 1. Admin → Marketplace → Pending Listings 2. Open listing 3. Review details (category, pricing, images, compliance) 4. Click Approve | Listing status changes to Approved | Not started | Pending Testing | Pending Recommendation |  | 2025-08-12 | In-progress | Pending Recommendation |  | 2025-11-26
IA-CM02-F09-TC02 | Reject (Deapprove) Product Listing | Listing pending | 1. Open listing 2. Click on reject 3. Confirm | Listing status set to Rejected; | Not started | Pending Testing | Pending Recommendation |  | 2025-08-12 | In-progress | Pending Recommendation |  | 2025-11-26
IA-CM02-F09-TC03 | Re-submit Rejected Listing | Listing rejected | 1. Seller edits listing 2. Resubmits | Status changes to Pending Approval | Not started | Pending Testing | Pending Recommendation |  | 2025-08-12 | In-progress | Pending Recommendation |  | 2025-11-26
IA-CM02-F09-TC04 | Bulk Approval of Listings | Multiple pending listings | 1. Select multiple listings 2. Click Approve | All selected listings approved | Not started | Pending Testing | Pending Recommendation |  | 2025-08-12 | In-progress | Pending Recommendation |  | 2025-11-26
IA-CM02-F09-TC05 | Publish Approved Listing | Listing approved | 1. Click Publish | Listing visible on marketplace | Not started | Pending Testing | Pending Recommendation |  | 2025-08-12 | In-progress | Pending Recommendation |  | 2025-11-26
IA-CM02-F09-TC06 | Unpublish Listing | Listing published | 1. Click Unpublish | Listing hidden but retained | Not started | Pending Testing | Pending Recommendation |  | 2025-08-12 | In-progress | Pending Recommendation |  | 2025-11-26
IA-CM02-F09-TC07 | Republish Unpublished Listing | Listing unpublished | 1. Click Publish | Listing visible again | Not started | Pending Testing | Pending Recommendation |  | 2025-08-12 | In-progress | Pending Recommendation |  | 2025-11-26
IA-CM02-F09-TC08 | Auto-Unpublish on Category, sub-category and commodity Deactivation | Category, sub-category and commodity deactivated | 1. Deactivate category, sub-category or commodity | All listings unpublished | Not started | Pending Testing | Pending Recommendation |  | 2025-08-12 | In-progress | Pending Recommendation |  | 2025-11-26
IA-CM02-F09-TC09 | Deactivate Active Listing | Listing active | 1. Select listing 2.Click Deactivate | Listing suspended and hidden | Not started | Pending Testing | Pending Recommendation |  | 2025-08-12 | In-progress | Pending Recommendation |  | 2025-11-26
IA-CM02-F09-TC10 | Reactivate Deactivated Listing | Listing deactivated | 1. Select listing 2.Click Activate | Listing restored | Not started | Pending Testing | Pending Recommendation |  | 2025-08-12 | In-progress | Pending Recommendation |  | 2025-11-26
IA-CM02-F09-TC11 | Auto-Deactivate Listings on Seller Suspension | Seller suspended | 1. Suspend seller | All listings deactivated | Not started | Pending Testing | Pending Recommendation |  | 2025-08-12 | In-progress | Pending Recommendation |  | 2025-11-26
IA-CM02-F09-TC12 | Auto-Deactivate on Association Suspension | Association suspended | 1. Suspend association | Listings deactivated | Not started | Pending Testing | Pending Recommendation |  | 2025-08-12 | In-progress | Pending Recommendation |  | 2025-11-26
IA-CM02-F09-TC13 | Set Listing as Featured | Listing published | 1. Select listing 2.Click Set Featured | Listing marked as featured | Not started | Pending Testing | Pending Recommendation |  | 2025-08-12 | In-progress | Pending Recommendation |  | 2025-11-26
IA-CM02-F09-TC14 | Verify Featured Visibility | Listing featured | 1. View homepage/featured section | Listing displayed | Not started | Pending Testing | Pending Recommendation |  | 2025-08-12 | In-progress | Pending Recommendation |  | 2025-11-26
IA-CM02-F09-TC15 | Remove Featured Status | Listing featured | 1. Select listing 2.Click Remove Featured | Featured flag removed | Not started | Pending Testing | Pending Recommendation |  | 2025-08-12 | In-progress | Pending Recommendation |  | 2025-11-26
IA-CM02-F09-TC16 | Auto-Remove Featured on Unpublish | Listing unpublished | 1. Unpublish listing | Featured status removed | Not started | Pending Testing | Pending Recommendation |  | 2025-08-12 | In-progress | Pending Recommendation |  | 2025-11-26
IA-CM02-F09-TC17 | Enforce Featured Limit | Featured limit set | 1. Feature beyond limit | System blocks or warns | Not started | Pending Testing | Pending Recommendation |  | 2025-08-12 | In-progress | Pending Recommendation |  | 2025-11-26
IA-CM02-F09-TC18 | Approval Notification | Notifications enabled | 1. Approve listing | Seller receives notification | Not started | Pending Testing | Pending Recommendation |  | 2025-08-12 | In-progress | Pending Recommendation |  | 2025-11-26
IA-CM02-F09-TC19 | Rejection Notification | Notifications enabled | 1. Reject listing | Seller receives notification | Not started | Pending Testing | Pending Recommendation |  | 2025-08-12 | In-progress | Pending Recommendation |  | 2025-11-26
IA-CM02-F09-TC20 | Activate notification | Notifications enabled | 1. Activate listing | Seller receives notification | Not started | Pending Testing | Pending Recommendation |  | 2025-08-12 | In-progress | Pending Recommendation |  | 2025-11-26
IA-CM02-F09-TC21 | Deactivate notification | Notifications enabled | 1.Deactivate listing | Seller receives notification | Not started | Pending Testing | Pending Recommendation |  | 2025-08-12 | In-progress | Pending Recommendation |  | 2025-11-26
IA-CM02-F09-TC22 | Publish Notification | Notifications enabled | 1. Publish listing | Seller notified | Not started | Pending Testing | Pending Recommendation |  | 2025-08-12 | In-progress | Pending Recommendation |  | 2025-11-26
IA-CM02-F09-TC23 | Featured Notification | Notifications enabled | 1. Feature listing | Seller notified | Not started | Pending Testing | Pending Recommendation |  | 2025-08-12 | In-progress | Pending Recommendation |  | 2025-11-26
ADMIN ORDER MANAGEMENT
IA-CM02-F08-TC01 | View Newly Placed Order | Buyer places order | 1. Admin → Orders 2. Filter by Pending | Order displayed with correct details | Not started | Pending Testing | Pending Recommendation |  | 2025-08-12 | In-progress | Pending Recommendation |  | 2025-11-26
IA-CM02-F08-TC02 | Validate Order Details | Order pending | 1. Open order | Product, unit, price, totals accurate | Not started | Pending Testing | Pending Recommendation |  | 2025-08-12 | In-progress | Pending Recommendation |  | 2025-11-26
IA-CM02-F08-TC03 | Default Status Validation | Order submitted | 1. Check status | Status = Pending | Not started | Pending Testing | Pending Recommendation |  | 2025-08-12 | In-progress | Pending Recommendation |  | 2025-11-26
IA-CM02-F08-TC04 | Seller Confirms Order | Order pending | 1. Seller confirms | Status → Confirmed | Not started | Pending Testing | Pending Recommendation |  | 2025-08-12 | In-progress | Pending Recommendation |  | 2025-11-26
IA-CM02-F08-TC05 | Admin Confirms Order on Behalf of Seller | Order pending | 1. Admin updates status to Confirmed | Status updated; | Not started | Pending Testing | Pending Recommendation |  | 2025-08-12 | In-progress | Pending Recommendation |  | 2025-11-26
IA-CM02-F08-TC06 | Prevent Confirmation of Rejected Order | Order rejected | 1. Admin Attempt to confirm | Action blocked | Not started | Pending Testing | Pending Recommendation |  | 2025-08-12 | In-progress | Pending Recommendation |  | 2025-11-26
IA-CM02-F08-TC07 | Confirmed Order Notification | Notifications enabled | 1. Admin Confirm order | Buyer notified | Not started | Pending Testing | Pending Recommendation |  | 2025-08-12 | In-progress | Pending Recommendation |  | 2025-11-26
IA-CM02-F08-TC08 | Seller Rejects Order | Order pending | 1. Seller rejects with reason | Status → Rejected | Not started | Pending Testing | Pending Recommendation |  | 2025-08-12 | In-progress | Pending Recommendation |  | 2025-11-26
IA-CM02-F08-TC09 | Admin Rejects Order | Order pending | 1. Admin updates status to Rejected 2. Provide reason | Status updated; buyer notified | Not started | Pending Testing | Pending Recommendation |  | 2025-08-12 | In-progress | Pending Recommendation |  | 2025-11-26
IA-CM02-F08-TC10 | Prevent Rejection After Confirmation | Order confirmed | 1. Attempt reject | Action blocked | Not started | Pending Testing | Pending Recommendation |  | 2025-08-12 | In-progress | Pending Recommendation |  | 2025-11-26
IA-CM02-F08-TC11 | Rejection Notification | Notifications enabled | 1. Admin Reject order | Buyer notified | Not started | Pending Testing | Pending Recommendation |  | 2025-08-12 | In-progress | Pending Recommendation |  | 2025-11-26
IA-CM02-F08-TC12 | Buyer Cancels Pending Order | Order pending | 1. Buyer cancels | Status → Cancelled | Not started | Pending Testing | Pending Recommendation |  | 2025-08-12 | In-progress | Pending Recommendation |  | 2025-11-26
IA-CM02-F08-TC13 | Seller Cancels confirmed Order | Order confirmed | 1. Seller cancels | Status → Cancelled | Not started | Pending Testing | Pending Recommendation |  | 2025-08-12 | In-progress | Pending Recommendation |  | 2025-11-26
IA-CM02-F08-TC14 | Admin Cancel confirmed order | Order pending | 1. Admin updates status to Cancelled | Status updated | Not started | Pending Testing | Pending Recommendation |  | 2025-08-12 | In-progress | Pending Recommendation |  | 2025-11-26
IA-CM02-F08-TC15 | Admin Cancels Confirmed Order | Order confirmed | 1. Admin cancels 2. Provide justification | Status → Cancelled | Not started | Pending Testing | Pending Recommendation |  | 2025-08-12 | In-progress | Pending Recommendation |  | 2025-11-26
IA-CM02-F08-TC16 | Prevent Cancellation After Delivery | Order delivered | 1. Attempt cancel | Action blocked | Not started | Pending Testing | Pending Recommendation |  | 2025-08-12 | In-progress | Pending Recommendation |  | 2025-11-26
IA-CM02-F08-TC17 | Cancellation Notification | Notifications enabled | 1. Cancel order | Buyer & seller notified | Not started | Pending Testing | Pending Recommendation |  | 2025-08-12 | In-progress | Pending Recommendation |  | 2025-11-26
IA-CM02-F08-TC18 | Seller Marks Order as Delivered | Order confirmed | 1. Seller updates status | Status → Delivered, buyer prompted to rate and review | Not started | Pending Testing | Pending Recommendation |  | 2025-08-12 | In-progress | Pending Recommendation |  | 2025-11-26
IA-CM02-F08-TC19 | Admin Marks Order as Delivered | Order confirmed | 1. Admin updates status to Delivered 2. Add delivery note | Status updated, buyer prompted to rate and review | Not started | Pending Testing | Pending Recommendation |  | 2025-08-12 | In-progress | Pending Recommendation |  | 2025-11-26
EMAIL AND SMS TEMPLATE CONFIGURATION | [8 empty] | 2025-08-12 | In-progress | Pending Recommendation |  | 2025-11-26
IA-FM01-F22-TC01 | View list of email Templates | Templates exists | 1. Open email template | List of email templates displays | Not started | Pending Testing | Pending Recommendation |  | 2025-08-12 | In-progress | Pending Recommendation |  | 2025-11-26
IA-FM01-F22-TC02 | Edit Email Subject | Template exists | 1. Open email template 2. Edit subject 3. Save | Subject updated | Not started | Pending Testing | Pending Recommendation |  | 2025-08-12 | In-progress | Pending Recommendation |  | 2025-11-26
IA-FM01-F22-TC03 | Insert valid Variable in subject | Template open, variable exist | 1. Add {{valid_var}} | Subject updated | Not started | Pending Testing | Pending Recommendation |  | 2025-08-12 | In-progress | Pending Recommendation |  | 2025-11-26
IA-FM01-F22-TC04 | Insert Invalid Variable in subject | Template open | 1. Add {{invalid_var}} | Subject updated | Not started | Pending Testing | Pending Recommendation |  | 2025-08-12 | In-progress | Pending Recommendation |  | 2025-11-26
IA-FM01-F22-TC05 | Edit Email Body Content | Template exists | 1. Update body text | Changes saved | Not started | Pending Testing | Pending Recommendation |  | 2025-08-12 | In-progress | Pending Recommendation |  | 2025-11-26
IA-FM01-F22-TC06 | Insert valid Variable in Body content | Template exists, variable exist | 1. Add {{valid_var}} | Updated body content | Not started | Pending Testing | Pending Recommendation |  | 2025-08-12 | In-progress | Pending Recommendation |  | 2025-11-26
IA-FM01-F22-TC07 | Multiple Variables in email template | Variables exist | 1. Add multiple variables | All accepted | Not started | Pending Testing | Pending Recommendation |  | 2025-08-12 | In-progress | Pending Recommendation |  | 2025-11-26
IA-FM01-F22-TC08 | Insert Invalid Variable in Body Content | Template open | 1. Add {{invalid_var}} | Body updated | Not started | Pending Testing | Pending Recommendation |  | 2025-08-12 | In-progress | Pending Recommendation |  | 2025-11-26
IA-FM01-F22-TC09 | Edit SMS Content | Template exists | 1. Open SMS template 2. Edit message | Saved successfully | Not started | Pending Testing | Pending Recommendation |  | 2025-08-12 | In-progress | Pending Recommendation |  | 2025-11-26
IA-FM01-F22-TC10 | Enforce SMS Character Limit | Limit configured | 1. Exceed limit | Warning displayed | Not started | Pending Testing | Pending Recommendation |  | 2025-08-12 | In-progress | Pending Recommendation |  | 2025-11-26
IA-FM01-F22-TC11 | Insert Invalid Variable in SMS | Template open | 1. Add {{invalid_var}} | SMS template updated | Not started | Pending Testing | Pending Recommendation |  | 2025-08-12 | In-progress | Pending Recommendation |  | 2025-11-26
IA-FM01-F22-TC12 | Insert valid Variable in SMS | Template open | 1. Add {{valid_var}} | SMS template updated | Not started | Pending Testing | Pending Recommendation |  | 2025-08-12 | In-progress | Pending Recommendation |  | 2025-11-26
IA-FM01-F22-TC13 | Auto-Split Long SMS (if supported) | Auto-split enabled | 1. Exceed limit | SMS split correctly | Not started | Pending Testing | Pending Recommendation |  | 2025-08-12 | In-progress | Pending Recommendation |  | 2025-11-26
IA-FM01-F22-TC14 | Prevent Empty SMS | Template open | 1. Remove content | Save blocked | Not started | Pending Testing | Pending Recommendation |  | 2025-08-12 | In-progress | Pending Recommendation |  | 2025-11-26
IA-FM01-F22-TC15 | Multiple Variables in Template | Variables exist | 1. Add multiple variables | All accepted | Not started | Pending Testing | Pending Recommendation |  | 2025-08-12 | In-progress | Pending Recommendation |  | 2025-11-26
IA-FM01-F22-TC16 | Variable Preview Resolution | Sample data exists | 1. Preview template | Variables resolved | Not started | Pending Testing | Pending Recommendation |  | 2025-08-12 | In-progress | Pending Recommendation |  | 2025-11-26